BANQUET HALL BOOKING SYSTEM Smart Venue Reservation & Event Management Platform

| 📅 Phase 5 — Project Planning & Scheduling | Agile Scrum ¦ Sprint Breakdown ¦ Gantt Roadmap |
| --- | --- |

5.1 Project Planning Overview

The project is organized using an Agile Scrum methodology with 2-week sprints. The overall timeline spans 16 weeks divided into four major phases. Continuous integration and delivery (CI/CD) practices are followed throughout the development lifecycle.

Project Timeline Roadmap

| Phase 1 Research & Requirements (Wk 1–3) | → | Phase 2 UI/UX Design & Prototyping (Wk 4–6) | → | Phase 3 Core Development (Wk 7–11) |
| --- | --- | --- | --- | --- |

| Phase 4 Integration & Testing (Wk 12–14) | → | Phase 5 UAT & Bug Fixes (Wk 15) | → | Phase 6 Deployment & Go-Live (Wk 16) |
| --- | --- | --- | --- | --- |

Sprint Breakdown

| Sprint | Deliverables | Duration |
| --- | --- | --- |
| S1 | Project setup, database schema design, user authentication module (JWT + bcrypt + OAuth2). | Weeks 1–2 |
| S2 | Hall listing APIs, search and filter engine, venue manager portal (listing management). | Weeks 3–4 |
| S3 | Booking engine, real-time availability calendar, package management and pricing module. | Weeks 5–6 |
| S4 | Payment gateway integration (Razorpay/Stripe), invoice generation, email/SMS notification system. | Weeks 7–8 |
| S5 | Post-event reviews & ratings module, analytics dashboard, admin panel, and final regression testing. | Weeks 9–10 |

Milestones & Deliverables

| Milestone | Description | Week |
| --- | --- | --- |
| M1 — Kickoff | Project charter signed, team roles assigned, development environment set up. | Week 1 |
| M2 — Design Complete | Figma wireframes and high-fidelity prototypes approved by stakeholders. | Week 6 |
| M3 — Core MVP | Booking and payment flow functional end-to-end in staging environment. | Week 11 |
| M4 — Testing Sign-off | All test cases passed; critical bugs resolved; performance benchmarks met. | Week 14 |
| M5 — UAT Complete | User acceptance testing completed with 92%+ task success rate. | Week 15 |
| M6 — Go-Live | Production deployment, DNS configuration, monitoring dashboards live. | Week 16 |

Banquet Hall Booking System ¦ Phase 5: Project Planning & Scheduling ¦ team@banquetbooking.dev